# Continuous
Improvement Plan

# Guidance and Templates

Version 3.0

April 2021

Contents

SECTION I. Developing a Continuous Improvement Plan	3

Farmer Engagement is the Foundation of the CIP	3

Steps of the Continuous Improvement Plan	4

Step 1. 	Identify Priority Topic Areas or FSA Questions	5

Step 2. 	Establish Targets	7

Step 3. 	Develop Activities to Achieve Targets	10

Step 4. 	Confirm the Timeline and Ensure Accountability	11

Step 5. 	Monitoring and Adjustment	11

CIP Template	11

Examples	13

SECTION II. Optimizing Farmer Engagement and Outreach in the Continuous Improvement Plan Process	19

Creating a Safe Space for Innovation and Improvement	19

Developing the Plan: Collaboratively Identifying Priorities and Targets	19

Implementing the Plan: Ongoing Farmer Engagement and Outreach	21

Monitoring the Plan: Achievements and Learning	22

SECTION III. Continuous Improvement Plan Template	23

(1)	Farm Management Group Information	23

(2)	Priorities, Targets and Associated Activities	24

(3)	Monitoring and Adjustment	26

SECTION IV. Continuous Improvement Plan – Progress Report Template	27

(1)	Farm Management Group Information	27

(2)	Priorities, Targets and Associated Activities	28

(3)	Monitoring and Adjustment	29

(4)	Upcoming Plans	29

# SECTION I. Developing a Continuous Improvement Plan

This document provides guidance for Farm Sustainability Assessment (FSA) users on how to develop a Continuous Improvement Plan (CIP). The guidance has been created with a focus on the process for Farm Management Groups (FMGs). The approach can be adapted for stand-alone farms, although some aspects of this document (e.g., outreach and engagement with farmers in a group) are only applicable to farm groups.

The CIP process is designed to be flexible rather than rigid and overly prescriptive. This flexible design allows for multiple pathways for addressing continuous improvement priorities and targets identified as part of the process. It is important to acknowledge that targets may not always be met and that plans may be changed based on lessons learned. In some cases, a farm or FMG may already have plans or preexisting activities that are aligned with the FSA continuous improvement model as outlined in this document. In those cases, the FSA user is encouraged to adapt their existing projects to what is described in this document to better support efforts for making improvements to their supply chain.

Templates for developing a CIP and reporting progress against the CIP are annexed separately. These resources provide a framework for FSA continuous improvement which includes the development and implementation of a CIP.

## Farmer Engagement is the Foundation of the CIP

Effective engagement with farmers or farm managers in developing the CIP will build trust to create a safe space for innovation and improvement. Using effective stakeholder engagement techniques, FMG Coordinators and farmers or farm managers can identify priorities and targets that will generate the most value for all members of the FMG. Sustaining this level of engagement will be critical in ensuring success of the CIP on an ongoing basis. More information on farmer engagement is provided in the accompanying document on optimizing farmer engagement and outreach.

## Steps of the Continuous Improvement Plan

The process to develop a CIP is described as a sequence of steps. These steps are designed to be flexible and can be adapted to the specific needs associated with each farm or FMG.

Set the main priority by FSA Topic area

Priorities

Establish baseline and measurable targets

Targets

Develop activities to achieve targets

Activities

Confirm timing and persons responsible

Timeline

Check progress towards targets and adjust

Monitoring

Fig 1: Summary of steps to develop the FSA Continuous Improvement Plan.

Step 1

## Step 1. 	Identify Priority Topic Areas or FSA Questions

Stakeholder Review and Discussion

Priority Topics or FSA Questions

Define Priority Topics

with Priority Screening Tool

Identify Performance Gaps

with Self-Assessment Questionnaire

Priority Screening Tool and FSA Self-Assessment Questionnaire Output. The first step in the process of developing a CIP is to identify the priority topics or FSA questions that will be the focus of continuous improvement. The Priority Screening Tool should be used to identify the priority topic areas, and results from the FMG’s FSA Self-Assessment Questionnaires can be used to understand performance gaps. The Continuous Improvement Plan can therefore be developed using the output of the Self-Assessment Questionnaires and/or the Priority Screening Tool.

Fig. 2: Summary of process for identifying priority topic area(s) or FSA question(s).

Stakeholder Engagement. The FMG Coordinator or other individuals responsible for developing the CIP should prepare a summary of potential priority topic areas and/or FSA questions that are most relevant to the FMG and that can be used to inform targeted stakeholder engagement. It is envisioned that this summary will be used as a basis for discussion with farmers in the Farm Management Group or relevant stakeholders (e.g., buyers, community members) to help confirm what would be a suitable topic area or FSA questions to prioritize for the CIP.

List of Priority Topics from the Priority Screening Tool

Air Quality

Biodiversity

GHG Emissions

Integrated Pest Management

Labour Conditions

Nutrient Management

Soil Conservation

Soil Health

Water Management

Waste Management

The output from this first step will be one or more priority topic areas or FSA questions that would serve as the basis for developing the CIP, and that have been prioritized based on discussions with farmers and other stakeholders. The discussions with farmers and other stakeholders should also help determine the specific targets that will form the basis of the CIP as part of Step 2.

If priority topics are selected for the basis of the CIP that are different from the main topics highlighted from the Priority Screening Tool, the justification for the decision should be included in the CIP template. As an example, some priority topics and their related targets may not be possible due to prohibitively high costs of implementation. In those circumstances, FSA users are encouraged to review targets based on their cost/benefit to select a priority or target that is more suitable for balancing the available resources of the FMG with potential for positive impact.

Step 2

## Step 2. 	Establish Targets

Using the summary of priority topics or FSA questions established in the first step, one or more specific targets should be established. There is no requirement as part of the CIP guidance on how many targets to develop. As a minimum, one target will need to be established, but depending on the FMG and priority topics identified in Step 1, more than one target could be included in the CIP.

Potential targets may have already been identified or suggested in Step 1 through the process of identifying priority topics or FSA questions from the Priority Screening Tool and Self-Assessment Questionnaires, or the FMG may have already defined targets through a separate process. In any case, details from the Priority Screening Tool or Self-Assessment Questionnaire will help in establishing targets.

Targets should be outcome-based, relevant, achievable, time-bound, and measurable.

Example

Some examples of measurable and time-bound targets include:

100% of farmers responding “yes” to FSA question 42 by 2022

100% of farmers achieve Silver-level of performance by 2022

Improve water-use efficiency on irrigated crops by 10% by 2025

Reduce farm-level GHG emissions by 20% by 2025

Some measurable targets may require the FMG or farm to establish a calculation approach and define a baseline. The calculation approach may require use of an outcome measurement tool, although the use of outcome measurement is not a necessary requirement of the CIP. If outcome measurement is needed as a component of the CIP, FSA users can refer to SAI Platform Guidance for supporting selection of the appropriate outcome measurement tool. Establishing a baseline could be the first part of a CIP and, in some cases, would require enough time for the FMG or farm to gather sufficient data to develop the baseline and accompanying target. A baseline is not required for all targets and will depend on the specifics of the CIP approach.

Risk vs Reward

Time Horizon

Level of Innovation

Bold goals
with high risk

Goals with greater chance of success but less impact

Shorter time-period & more achievable targets

Longer time horizon with more potential for innovation

Fixed target which then defines the need for specific activities

Exploration as first step to refocus potential target later

Considerations for Setting Targets

Fig. 3: Example trade-offs to consider when establishing targets.

Balancing Risk and Reward. As part of the process of identifying priorities and setting targets, the FMG or farm may be faced with the decision of pursuing bold goals with high risk or choosing targets that have greater chances of success but less potential impact. Both approaches can have merit and ultimately the choice between risk and reward of the CIP will be for the FMG or farm to determine based on their specific context and situation.

Time Horizons. For those participants that are just getting started, one approach may be to think creatively and ambitiously by considering targets with a longer time horizon (e.g., 10 years) and more challenges in implementation but that can inform incremental targets within the three-year period of their CIP. In other cases, a shorter time-period to achieve targets may be more appropriate and achievable.

The Right Level of Innovation. Continuous improvement can require innovative solutions that need experimentation to get right. In some cases, a FMG or farm may know the target they want to achieve but not the details of which activities are required to achieve it. In other cases, even the end target may be less clear, and the first step would be some exploration to better understand what the FMG or farm should focus on. FSA users are encouraged to adopt an approach that works best for their specific context. The process of establishing targets may be experimental and iterative, requiring the FMG or farm to re-adjust along the way.

Activity 1

Due Date

Person Responsible

YYYY-MM-DD

Name, Position

Activity 2

Due Date

Person Responsible

YYYY-MM-DD

Name, Position

Activity 3

Due Date

Person Responsible

YYYY-MM-DD

Name, Position

Target

Due Date

YYYY-MM-DD

Step 3. 	Develop Activities to Achieve Targets

Step 3

Fig. 4: Example of an arrangement of target, associated activities, due dates, and responsible parties.

Once targets are developed, related activities will need to be identified to support achieving them. Activities reflect specific actions and strategies that when implemented will allow the FMG or farm to reach the target. For example, the CIP target may be to reduce water use on irrigated farms within the FMG by 20%. Examples of supporting activities to achieve that target could include that farmers are trained on testing distribution uniformity of their irrigation system, and some of the farmers in the FMG change their irrigation system from sprinklers to drip. It is recommended that activities should have a measurable component. In the example of a target related to water use, that might be that 40% of farmers are trained on testing their irrigation system, and 25% of farmers install a new drip-irrigation system.

The impact or effectiveness of activities on achieving targets will need to be reviewed on an ongoing basis to ensure that desired outcomes are achieved. In some cases, it will be necessary to adjust activities and/or their associated measurable results. This aspect is also covered in Step 5, Monitoring and Adjustment.

Step 4

## Step 4. 	Confirm the Timeline and Ensure Accountability

When developing the activities associated with CIP targets, it will be necessary to create an associated timeline and assign individuals to be responsible for carrying out the activities. For example, the activity of “training 40% of farmers on testing their irrigation system” could be assigned to the agronomist and outreach manager that works on the behalf of the FMG, with a deadline of completing the training prior to the next growing season. Timelines will vary depending on features of the FMG or farm (e.g., whether crop is annual or perennial) as well as the details of the targets and activities defined in the CIP.

## Step 5. 	Monitoring and Adjustment

Step 5

An ongoing mechanism will need to be developed as part of the CIP to monitor the effectiveness of activities as well as relevance and achievability of the targets. The primary goal of the CIP is to encourage engagement of the FMG and farmers in making positive improvements for the sustainability of their operations. If monitoring activities indicate this overarching goal is not being met, then the FMG is encouraged to change or update the approach.

## CIP Template

The steps outlined above are summarized in the FSA Continuous Improvement Plan Template. FMGs and stand-alone farms will be required to provide evidence demonstrating their Continuous Improvement Plan Template has been completed at the time of the verification audit.

Progress Reporting

Although FMGs or stand-alone farms are not required to submit progress reports to SAI Platform or their verification body, they should maintain internal records at their operation. The auditor conducting the verification may request examples of progress reports during a re-verification audit.

Internal reporting on progress against the CIP will be required at least once every year, as informed by the monitoring and adjustment step of the CIP. Depending on the specific target and activities, the FMG may choose to review and report progress on a more frequent basis.

Progress reporting should be done using the CIP Progress Reporting Template. In most cases, progress reporting will be arranged by the FMG Coordinator by gathering information from individuals responsible for carrying out the activities defined in the CIP. Progress reports should include details on progress of their activities, including quantitative information where possible. For example, for the activity of training 40% of farmers on testing their irrigation system, the progress report should include the percentage of farmers trained to-date. In some cases, it may be necessary to describe ongoing success with the project without reference to metrics, as would be the case if the first part of the project is setting a baseline that will serve as a foundation for establishing a target.

Verification Audit

While the verification auditor will not be responsible to evaluate the quality or feasibility of the CIP, they will review the following components of the CIP template to ensure that a CIP is in place, as part of the FSA Management System Verification Audit:

Priority areas and targets have been defined

Justification in case that priority topics were selected that differ from the output of Priority Screening Tool (if applicable)

Evidence that farmers were actively engaged in the development of the CIP

Management responsibilities for the CIP clearly assigned

Annual Management review process to review progress against the CIP

Timeline for achieving targets has been agreed

This is only a mandatory requirement for verification of Farm Management Groups and is a voluntary requirement for Stand-Alone Farms. The Audit Control Points for FSA Management Audits specify the evidence the auditor will be evaluating.

The auditor will also discuss any relevant observations related to the CIP with the FMG Coordinator or other individuals, e.g. if there is adequate resourcing in terms of materials and budget, how the monitoring plan may be improved, discussion about the associated costs of activities proposed and broadly confirming those are realistic (e.g., if replacing equipment, implementing new technologies, etc.) as well as ensuring that individuals with responsibilities for the CIP will be available and have time to support the CIP process.

The results of the verification audit may suggest revisions or updates to the CIP. For example, some FSA questions or farm management areas may be highlighted as areas of improvement based on the verification auditor’s review. If there is an outcome from the verification audit that might lead the FMG to revise the CIP (e.g., based on verification auditor feedback on performance against the Self-Assessment Questionnaires), then the FMG representative responsible for the CIP is encouraged to go through the development steps again to revise their CIP, including re-engagement with the farmers in the FMG as needed to confirm priorities.

## Examples

Examples of the CIP are provided in the tables below. These short examples are provided for guidance purposes only to help FMGs or stand-alone farms in thinking about their own CIP, but the approach for any FMG or farm will be specific to their particular context.

| Example 1 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Continuous Improvement Planning related to FSA Question 28: Maintenance of Cover Crop, Increase of Organic Matter, Protect and Promote Soil Biodiversity |  |  |  |  |
| Target: 100% farmers answer “Yes” to FSA 28 (cover crops, soil organic matter, soil biodiversity) |  |  |  |  |
| Year | 1 |  | 2 | 3 |
| Actions | Education/ outreach on cover crops Identification of model farms Financial support to purchase cover crop seed |  | Financial support to purchase cover crop seed | Surveys of participating farmers and monitoring of soil organic matter |
| Step |  | Details |  |  |
| Priority Topic |  | - Topic area of Soil Health was identified by Priority Screening, and most farmers responded “No” to FSA 28 indicating that few farmers were maintaining cover crops. |  |  |
| Target |  | - The main target will be for 100% farmers to answer “Yes” to FSA 28 related to cover crops, soil organic matter, and soil biodiversity. This will be done by the time of the next verification cycle. |  |  |
| Activities and Timeline |  | Activity 1: Education/Outreach with all farmers in the FMG on how to establish cover crops, with associated information on soil organic matter and soil biodiversity (Year 1-2). Person Responsible: Education and Outreach Manager. Activity 2: Identify 5 model farms that could demonstrate methods and benefits of growing cover crops (Year 1). Person Responsible: Education and Outreach Manager. Activity 3: Financial support for growers in obtaining cover crop seed (Years 1 and 2). Person Responsible: FMG Manager; Representative from local agricultural service provider. Review success of education and outreach events through surveys of participating farmers after 6 months. Person Responsible: Education and Outreach Manager. Targeted monitoring of soil organic matter on 10% of farms with and without cover crop to test effectiveness of cover crop implementation; review on a quarterly basis. Person Responsible: Education and Outreach Manager. |  |  |

| Example 2 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Continuous Improvement Planning related to Water Management. |  |  |  |  |
| Target: Reduce water used in the farm management group by 10% |  |  |  |  |
| Year | 1 |  | 2 | 3 |
| Actions | Outreach and identification of farmer participants |  | Financial and technical support for drip line installation for 30% of farmers | Surveys of participating farmers and monitoring of water use |
| Step |  | Details |  |  |
| Priority Topic |  | - Topic area of Blue Water was identified by Priority Screening, because most farmers rely on irrigation and the rate of extraction is greater than the replenishment capacity. |  |  |
| Target |  | - The main target will be for farmers to reduce the amount of water used for their annual crop by 10%. This target will be achieved in three years. |  |  |
| Activities and Timeline |  | The main activity associated with the target will be to increase adoption of drip irrigation technology from 40% of farmers now to 70%. Activity 1: Identify farmers in the FMG that would be interested in installing drip irrigation lines by end of Year 1. Person(s) Responsible: Outreach and Education Coordinator. Activity 2: Technical and financial support for farmers to install drip irrigation systems (Year 2). Person(s) Responsible: Outreach and Education Coordinator; Processing Facility Manager Activity 3: On an ongoing basis review amount of water used by farmers using drip irrigation compared to those using conventional irrigation to compare water-use. Ongoing review of research on irrigation techniques. Person(s) Responsible: FMG Manager. |  |  |

| Example 3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Continuous Improvement Planning related to GHG emissions. |  |  |  |  |  |
| Target: Reduce greenhouse gas emissions in the farm management group by X% |  |  |  |  |  |
| Year | 1 |  |  | 2 | 3 |
| Actions | Select GHG calculator tool Work with farmers to enter data in calculator tool and establish a baseline, with related target |  | Education and outreach on practices with emission reduction potential (e.g., no-till) Replacement of farm vehicles with electric alternatives (government program supported) Monitoring GHG emissions using calculator |  | Education and outreach on practices with emission reduction potential (e.g., no-till) Replacement of farm vehicles with electric alternatives (government program supported) Monitoring GHG emissions using calculator |
| Step |  | Details |  |  |  |
| Priority Topic |  | - Topic area of Air Quality and Emissions identified by Priority Screening, based on customer scan prioritizing need for information on GHGs and current lack of measurement to GHGs in the FMG. |  |  |  |
| Target |  | Baseline for GHG emissions has not yet been established. The FMG will use a GHG calculator to determine baseline in the first year of the project and set quantitative goal after that. The main target will be a percentage reduction of GHG emissions, to be achieved by time of re-verification audit. The exact target will be determined after baseline is established in Year 1. |  |  |  |
| Activities and Timeline |  | Activity 1: Establish baseline (Year 1). Person(s) Responsible: FMG Manager; Outreach and Education Coordinator. Activity 2: Education/outreach on practice identified from the baseline that could lead to reduced emissions (e.g., a potentially activity could be training with outcome of 50% of farmers adopting no or reduced till) (Year 2-3). Person(s) Responsible: Outreach and Education Coordinator. Activity 3: Replacement of farm vehicles with electric alternatives. Education/outreach with all farmers in the FMG on types of vehicles available and support to identify government programs that financially support transition to electric vehicles (Year 2-3). Person(s) Responsible: Outreach and Education Coordinator. Activity 4: On an ongoing basis review results from the GHG calculator after year 2 to confirm GHG reduction potential of reduced or no-till cultivation and impacts of reducing emissions from farm vehicles. Person(s) Responsible: FMG Manager; Outreach and Education Coordinator. |  |  |  |

# SECTION II. Optimizing Farmer Engagement and Outreach in the Continuous Improvement Plan Process

## Creating a Safe Space for Innovation and Improvement

Effective engagement with farmers or farm managers in developing the Continuous Improvement Plan (CIP) will build trust to create a safe space for innovation and improvement. Using techniques to engage farmers, a Farm Management Group (FMG) Coordinator can collaborate with farmers or farm managers to identify priorities and targets that can generate the most value for all members of the FMG.

The CIP process is designed to be flexible rather than rigid and overly prescriptive. This flexible design allows for multiple pathways to addressing continuous improvement priorities and targets identified by the FMG. It is important to acknowledge that targets may not always be met and that plans may be changed based on lessons learned.

## Developing the Plan: Collaboratively Identifying Priorities and Targets

A suggested initial step for collaboratively developing a CIP is for the FMG Coordinator or another representative of the FMG to engage a group of farmers in an inclusive discussion. This discussion could focus on one or more priority topics identified as relevant using the FSA Priority Screening Tool or from results of the FSA Self-Assessment Questionnaire. Ensuring that the group of farmers is representative of the overall FMG is an important consideration. Factors including the location and size of farms, gender of farmers, and crops produced, among other factors, should be considered by the FMG Coordinator when organizing group discussions.

Example

Example FMG Farmer Outreach Techniques to Generate Feedback:

Surveys or polls

Facilitated group discussions

Focus-groups

One-on-one meetings

Online outreach – emails or video

Once the FMG Coordinator has organized a representative group of farmers, they can use the output of the Priority Screening Tool and Self-Assessment Questionnaire as a basis for discussion with farmers. Receiving input from participating farmers is a critical aspect of the CIP process, as it will inform CIP priorities for the FMG. Engagement at this step can make use of a variety of formal and informal techniques to gather input, which may include the following:

Surveying and/or polling the farmer group to solicit feedback on specific FSA priorities;

Open-ended and close-ended question and answer sessions to facilitate discussion on different topics identified as priority areas; and/or,

Use of visual aids, such as presentations, or white boards to engage the group using visual cues.

Prior to meeting with farmers, the FMG Coordinator is encouraged to develop a summary of proposed priorities and potential targets to guide discussion on the CIP. This planning can serve to facilitate the conversation with farmers and ensure that feedback is received on all potential priorities and targets.

In some circumstances, it may be logistically difficult or impossible for the FMG Coordinator to organize meetings with a larger group of farmers. In these situations, the FMG Coordinator may still conduct farmer outreach to develop the CIP using one or more of the following strategies:

One-on-one meetings to review priority topics and solicit feedback;

Multiple focus groups each including 3-4 farmers; and/or,

Email outreach, mobile-enabled video calls, or structured feedback (e.g., online survey).

It is important to note that in the case of very large FMGs there may be a need to conduct facilitation with farmers with multiple FMG representatives. In those instances, the farmer engagement techniques can still be effectively used. Ultimately, this guidance should be adapted as needed to develop a CIP through effective engagement of a representative group of farmers.

## Implementing the Plan: Ongoing Farmer Engagement and Outreach

Sustaining the level of engagement as described above will be critical in ensuring success of the CIP on an ongoing basis. The FMG Coordinator and any team members responsible for the CIP are encouraged to maintain similar forms of engagement throughout the process of development and implementation of the CIP. Meetings, surveys, or other forms of engagement and outreach are encouraged with farmers as a basis for developing progress reports on a regular basis. In those cases, outreach or engagement may be more targeted as compared to the original process of creating the CIP, but ongoing feedback and discussion with farmers will be necessary to understand success of the plan as well as whether adjustments are needed.

Peer-to-Peer Learning

In addition to using techniques of in-person or virtual meetings and email or online outreach, ongoing training and engagement of farms in carrying out the CIP can also benefit from effective peer-to-peer learning and engagement. For example, establishing model or demonstration farms can be a useful technique of encouraging adoption of practices that are less well-known among the FMG or that may be perceived as risky. Peer-to-peer learning can also be encouraged using a ‘train-the-trainer’ approach by selecting specific farmers or farm managers for an initial training by the FMG Coordinator and that can further train other farms in the FMG. This type of approach can be used by identifying certain farmers or farm managers that can act as leaders or program advocates to support working with other farms on implementation.

Example

Examples of Peer-to-Peer Learning Approaches:

Demonstration plots

Train-the-trainer

Lead farmers

## Monitoring the Plan: Achievements and Learning

As an important part of ongoing farmer engagement and outreach, the FMG Coordinator should ensure that feedback is received from farmers on the CIP regarding challenges and where changes need to be made. In addition, the FMG Coordinator should ensure there are opportunities to share lessons learned in the process as well as to acknowledge the successes and achievements of the farms in the group that are making improvements according to the CIP.

# SECTION III. Continuous Improvement Plan Template

## Farm Management Group Information

Complete the general descriptive information in the table below for your Farm Management Group.

| Farm Management Group Information |  |
| --- | --- |
| Name of Farm Management Group (FMG) |  |
| Name and Address of FMG Coordinator |  |
| Name and Title of Primary Person Responsible for the Continuous Improvement Plan |  |
| Stakeholders Consulted in Creation of the Continuous Improvement Plan Include a summary of the stakeholder consultation process and examples of stakeholders that participated (e.g., farmers/farm managers, buyers, etc.) in the process of creating the Continuous Improvement Plan. |  |

## Priorities, Targets and Associated Activities

A priority topic area or FSA question may have one or more associated targets. Each target may have one or more associated activities. Complete as many worksheets per target area as needed for your Continuous Improvement Plan. It may be necessary to copy and paste this section of the CIP.

| CONTINUOUS IMPROVEMENT PLAN WORKSHEET (1/2) |  |  |  |
| --- | --- | --- | --- |
| Priority Topic Area or FSA Question(s) |  |  |  |
| Justification for Priority Topic or FSA Question(s) Provide a short description of reason for selecting priority or FSA question(s). Note reasons if priority was selected that was different from output of priority screening report. |  |  |  |
| Target |  | Target Due Date | (YYYY-MM-DD) |

| CONTINUOUS IMPROVEMENT PLAN WORKSHEET (2/2) |  |  |  |
| --- | --- | --- | --- |
| Activity | Due Date | Person Responsible | Notes |
|  | (YYYY-MM-DD) | (Name, Position) |  |
|  | (YYYY-MM-DD) | (Name, Position) |  |
|  | (YYYY-MM-DD) | (Name, Position) |  |
|  | (YYYY-MM-DD) | (Name, Position) |  |
|  | (YYYY-MM-DD) | (Name, Position) |  |
|  | (YYYY-MM-DD) | (Name, Position) |  |
|  | (YYYY-MM-DD) | (Name, Position) |  |
|  | (YYYY-MM-DD) | (Name, Position) |  |
|  | (YYYY-MM-DD) | (Name, Position) |  |
|  | (YYYY-MM-DD) | (Name, Position) |  |
|  | (YYYY-MM-DD) | (Name, Position) |  |
|  | (YYYY-MM-DD) | (Name, Position) |  |
|  | (YYYY-MM-DD) | (Name, Position) |  |

## Monitoring and Adjustment

This section should only be completed for those FSA users who are completing the CIP template during process of re-verification and whose CIP builds on their previous efforts.

| Monitoring and Adjustment |  |
| --- | --- |
| Summary of Changes to the CIP in the Previous 3-Year Period Include notes on challenges encountered as well as positive developments |  |

# SECTION IV. Continuous Improvement Plan – Progress Report Template

## Farm Management Group Information

Complete the general descriptive information in the table below for your Farm Management Group.

| Farm Management Group Information |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of Farm Management Group (FMG) |  |  |  |  |
| Name and Address of FMG Coordinator |  |  |  |  |
| Name and Title of Person Responsible for the Continuous Improvement Plan |  |  |  |  |
| Progress Reporting Period FSA users are encouraged to complete progress reports at least once every year. |  |  |  |  |
| Start Date | (YYYY-MM-DD) |  | End Date | (YYYY-MM-DD) |

## Priorities, Targets and Associated Activities

A priority topic area or FSA question may have one or more associated targets. Each target may have one or more associated activities. Complete as many worksheets per target area as needed for your Continuous Improvement Plan. It may be necessary to copy and paste this section of the CIP. The targets and activities listed below should follow from the description of your CIP as provided in your initial planning template.

| PROGRESS REPORTING WORKSHEET |  |  |
| --- | --- | --- |
| Priority Topic Area or FSA Question |  |  |
| Target | Estimated % completion to target: |  |
| Activity |  | Progress Made |
|  |  | Estimated % completion of the activity: |
|  |  | Estimated % completion of the activity: |
|  |  | Estimated % completion of the activity: |
|  |  | Estimated % completion of the activity: |
|  |  | Estimated % completion of the activity: |
|  |  | Estimated % completion of the activity: |
|  |  | Estimated % completion of the activity: |

## Monitoring and Adjustment

List primary challenges as well as opportunities that arose during the progress reporting period.  For challenges, list the activities that were undertaken to address them. For opportunities, provide information on how they impacted or changed your original planning.

| Monitoring and Adjustment |  |
| --- | --- |
| Type of Challenges or Opportunities | Adjustments to CIP |

## Upcoming Plans

List your main plans for the next year or upcoming progress reporting period.